## Grand Plan
Customer: |  | (Astemo)AM-GA | Open | P | GRAND PLAN | [15 empty] | Revision Tracking |  |  |  | Core Team
Supplier: |  |  | Closed | A | [16 empty] | No. | Date | Name |  | Name |  | Role
Part Name: | [24 empty] | Ex. Lindsey Grizzard |  | (Astemo)-Proc.
Part Number: | [5 empty] | Planned | Actual | Prototype | Pre-Launch | Production | Pass through | Customer Trial | Submit for Approval | Approval
Drawing Number:
Product Number
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Requirement: (Pcs/month) |  |  | Responsible | Status |  | 2022 | [21 empty] | 2023 | [11 empty] | Comments
[6 empty] | April |  |  |  | May |  |  |  | June | July | August | September | October | November | December |  |  | January | February |  | March |  | April | May | June | July | August | September | October | November | December | January | February | March
Overall Timing |  | Company
|  | Astemo AM GA | Customer-Sales |  | P | Actual
A
|  | Supplier | APQP-Team |  | P
A
Item |  | Task
1 | Request for APQP Team | Send PPAP Order Requirements | Astemo-Procurment |  | P
A
|  | Distribute Requirements & Set New Order Meeting | Supplier- Sales |  | P
A
2 | New Order Meeting | Review Customer Requirements- Complete Tab 2 | Supplier APQP-Team |  | P
A
|  | Produce Grand Plan | Supplier APQP-Team |  | P
A
|  | Assign Team Leader | Supplier-PE Mgr |  | P
A
|  | Action Item List & Follow-ups | Supplier Team Leader |  | P
A
|  | Send Grand Plan and Information Tab to Astemo | Supplier Team Leader |  | P
A
| Design Review | Deisgn FMEA | Supplier |  | P
A
|  | Design Review Meeting | Supplier |  | P
A
| Review Sourcing | Bulk Material Requirements | Supplier Purchasing |  | P
A
|  | Complete APQP Tab 1 and 3 | Supplier Purchasing |  | P
A
| Prepare Tooling | Create Detailed Plan, Complete APQP Tab 4 | Supplier- PE |  | P
A
| Prepare Gages & Fixtures | Create Detailed Plan, Complete APQP Tab 4 | Supplier- PE |  | P
A
| Prototype Build | Control Plan, Complete APQP Tab 5 | Supplier- PE |  | P
A
|  | Ship Prototype Parts (with prototype label) | Supplier |  | P
A
| PPAP Event | Review drawing and specifications; Identify critical dimensions, Complete APQP Tab 6 and 7 | Supplier |  | P
A
|  | Mfg. Process Flow Chart, Complete APQP Tab 8 |  |  | P
A
|  | Process FMEA, Complete APQP Tab 9 |  |  | P
A
|  | Measurement Systems Evaluation, Complete APQP Tab 10 |  |  | P
A
|  | PreLaunch Control Plan, Complete APQP Tab 11 |  |  | P
A
|  | Team Member Work Instructions, Complete APQP Tab 12 |  |  | P
A
|  | Production Trial Run, Complete APQP Tab 15 |  |  | P
A
|  | Dimensional Results N=5 |  |  | P
A
|  | Process Capaility Study, Complete APQP Tab 16 |  |  | P
A
|  | Appearance Approval Report |  |  | P
A
|  | Production Validation Study, Complete APQP Tab 17 |  |  | P
A
|  | Ship PPAP Parts, labeled |  |  | P
A
|  | Ship Sample Production Parts (N=5, labeled) |  |  | P
A
|  | Master Sample maintained at supplier site |  |  | P
A
|  | Checking Aids |  |  | P
A
| PPAP Documentation | ISO/TS16949/ISO14001 Certificates Sent to Supplier | Supplier |  | P
A
|  | ELV, RoHs, MSl, Termperature Profile, Leas Free Documentation |  |  | P
A
|  | Submit GA Specific Packaging Data Sheet, Complete APQP Tab 13 |  |  | P
A
|  | IMDS submited online, Company ID: 6785 |  |  | P
A
|  | Safe Launch Plan and Procedure |  |  | P
A
|  | Sub-Supplier Chain Matrix, Sub Supplier Readiness Status (PSWs, Material Certificaton, other supporting documents as required) |  |  | P
A
|  | AIAG CQI-9,11, 12, 15, 16, 17, 19, 23 Compliance Audit as required for specific purposes |  |  | P
A
|  | Bulk Material Requirements, Including MSDS |  |  | P
A
|  | Pricing Contract |  |  | P
A
|  | Run at Rate/ Capacity Studies, CAR (OEE), etc |  |  | P
A
|  | GA Specific Capacity Verification |  |  | P
A
|  | Certificate of Origin |  |  | P
A
|  | Part Submission Warrant, Complete APQP Tab 18 |  |  | P
A
| PPAP Submittal | PPAP Package | Suuplier QA |  | P
A
| PPAP Approval | Customer Follow-up | Suuplier QA |  | P
A
| Production Launch Meeting | Identify & Address Issues | APQP-Team |  | P
A
| Mass Production | Start | Supplier-Prod. |  | P
A
| Dissolve Team | Objective Met | APQP-Team |  | P
A
|  |  |  | Updated by Date: | [9 empty] | Ex. LG Reviewed 7/30/14 | [25 empty] | CONFIDENTAL

## APQP Status Report (linked)
Advanced Product Quality Planning Status Report
| Supplier/Org: |  |  |  |  | Program: |  | Part Name:
| Location: |  |  |  |  | Model Year: |  |  | Part Number:
| Supplier Code: | [7 empty] | Notice Level:
| Contact Name/Tel: |  |  |  |  | Review Date: |  |  | User Plant:
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
FPDS MILESTONE |  |  | VP | TT | PP | SOP
APQP ELEMENT |  | Date | 0 | 0 | 0 | 0
1. | Sourcing Decision |  | G | G | G
2. | Customer Input Requirements |  | Y | Y | Y | G
3. | Subcontractor APQP Status |  | G | G | G
4. | Facilities, Tools & Gages |  | G | G | G
5. | Prototype Build(s) |  | G | G | G
6. | Drawings & Specifications |  | G | G | G
7. | Team Feasibility Commitment |  | G | G | G
8. | Manufacturing Process Flowchart |  | G | G | G
9. | Process FMEA |  | G | G | G
10 | Measurement Systems Evaluation |  | G | G | G
11. | Pre-Launch Control Plan |  | G | G | G
12. | Operator Process Instructions |  | G | G | G
13. | Packaging Specifications |  | Y | Y | Y | G
14. | Production Trial Run |  | G | G | G
15. | Production Control Plan |  | G | G | G
16. | Preliminary Process Capability Study |  | G | G | G
17. | Production Validation Testing |  | G
18. | Part Submission Warrant (PSW) |  | G | G | G
OVERALL APQP STATUS RATING (GYR) |  |  | Y | Y | Y | G
Element / Activity |  | Issue(s) for Red/Yellow Elements |  |  |  | Corrective Action / Resolution Plan |  |  | Timing |  | Responsibility
# | Activity | (summarize the concern & resulting risk) |  |  |  | (e.g. revise timing, allocate resources) |  |  | Open | Close | Astemo-GA | Supplier
1
2
3
4
5
6
7
8
9
10
Ratings below are display-only and automatically linked to ratings on page 1 - do not enter data. See "Information" worksheet for additional Program, Team and Part Information.
FPDS MILESTONE |  |  | PT1 | PT2 | SOP | GP12
APQP ELEMENT |  |  | 2012-01-15 | 2012-04-01 | 2012-07-15 | 2012-09-12
OVERALL APQP STATUS RATING (GYR) |  |  | Y | Y | Y | G
Procurement |  | 09/30/2012 |  | QA |  |  | 12/27/12 | Design |  |  | 1/7/2013

## Information
INFORMATION WORKSHEET - APQP STATUS REPORTING
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
PROGRAM INFORMATION (dates will show up on linked APQP Status Report and individual checklists)
FPDS MILESTONES | Kick Off | VP | TT | PP | SOP
Enter Actual Dates >>
ic
Chief Engineer: |  |  | Other:
PART INFO & PSW COMMITMENT |  |  |  |  | CAPACITY REQ'TS |  |  | RUN-AT-RATE INFO
Part Number | Part Description | Notice Level | PSW Date 1 | PSW Date 2 | Max CPV Weekly | Ave CPV Weekly | Ave CPV/hr | Run@Rate Date | Duration (# hrs run) | Quantity (# pcs run) | # Parts/Hr Achieved | % 1st Yield | Pass (Y/N)
High Impact Supplier ? : |  | RISK INFORMATION (SITE, TECHNOLOGY, PROCESS, OTHER - HIGH IMPACT ??)
Risk 1 | High cost % of total program |  |  |  |  | VA/VE activity and pricing review
Risk 2
Risk 3
TEAM INFORMATION
Team Members | Company / Role | Tel# | Fax# |  | Email |  | Remarks
BUILD EVENT INFORMATION - PROTOTYPE | [5 empty] | BUILD EVENT INFORMATION - PRODUCTION
Build Event | QTY | MRD | # SCs | # CCs |  | Build Event |  | QTY |  | MRD |  | # SCS | # CCs
T1 |  | 0
T2 |  | 0
T3 |  | 0
T4 |  | 0
J1 |  | 0
ADDED STARTER
LOG OF CHANGES / SUPPLEMENTAL NOTES for STATUS REPORT
Element / Item | Description of Change/Item | [9 empty] | Date of Change/Item

## 1. Sourcing
|  |  | APQP Element Rating Checklist |  |  | Sourcing Decision is a formal customer commitment to work with all Internal & External Part Suppliers, Tooling Suppliers, and Facility Suppliers on the program. Suppliers, and their sub-suppliers, should be engaged as early as possible (e.g. by SC) to understand program timing and requirements. Sourcing Decision should be made with appropriate Quality History & Customer Input Data.
1. Sourcing Decision
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Sourcing Decision issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Ensure that the Supplier's Quality History is factored into the Sourcing Decision for all Phases of the Sourcing Decision including Global Logistics concerns. (e.g. Supplier Improvement Metrics (SIM) database). |  |  |  |  | G | G | G
3 | Complete and communicate the Sourcing Decisions to the Part, Tooling & Facility Suppliers/Sub-Suppliers by the SC Milestone. |  |  |  |  | G | G | G
4 | The Pricing Contract has been signed by Astemo AM GA Purchasing and the Supplier. |  |  |  |  | G | G | G
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 2. Customer Input
|  |  | APQP Element Rating Checklist |  |  | Customer Input Requirements are the design criteria and the program requirements necessary to initiate the APQP process. They include Design Goals, Reliability and Quality Goals, Program Timing, Affordable Cost Targets, Capacity Planning Volumes, Key Contact Personnel, and input requested from & supplied by the Manufacturing Facilities involved. This is done to assure that any current Manufacturing/Process issues are addressed appropriately by the new design and process, early in the Product Development cycle.
2. Customer Input Requirements
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Customer Input issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the cross-functional team that will be responsible for benchmarking similar vehicles, reviewing and analyzing the Quality Data and History, in support of the different target levels. Members should include representation from Quality/Reliability, Design Engineering, Manufacturing Engineering, Global Logistics and Manufacturing Planning & Logistics (MP&L), and the plants, etc. |  |  |  |  | G | G | G
3. | Develop a list of the key contact personnel within Astemo-GA and Suppliers, including names, locations, and phone numbers of the Program Managers, Design & Release Engineers, Purchasing Agent, STA Engineer, and others as appropriate.List on the 'Information' Tab |  |  |  |  | G | G | G
4. | Develop an "Action Matrix" from information requested by the Assembly, Stamping, and other applicable manufacturing organizations for data describing carry-over issues, current and potential manufacturing issues, etc., so that the issues can be addressed early by design and process improvements/actions. |  |  |  |  | G | G | G
5. | Analyze and understand appropriate function of the part relative to VTC. Areas to research include: Craftsmanship information, External Quality Indicators (Warranty/Customer Satisfaction), Campaigns (Recalls/Owner Notifications), Fresh Eyes History on outgoing vehicles, Manufacturing Capability (Cp/Cpk), Equipment Reliability & Maintainability (Machinery FMEA's, breakdowns/downtime, Preventive Maintenance information), Health/Safety/Ergonomics, carry-over issues (FCPA/NOVA -C Audits), First Run, and Repair, etc. |  |  |  |  | Y | Y | Y | g
6. | Use the Program's Timing Dates to create a plan for APQP requirements, Program Status Reviews, Design Freeze, Prototype Builds, Material Required Dates, and SOP. |  |  |  |  | G | G | G
7. | Prepare a Total Cost review for the applicable affordable cost targets, as they are defined for the Program, including peak volumes. |  |  |  |  | G | G | G
8. | Understand the Capacity Planning Volumes as they are defined for the Program. |  |  |  |  | G | G | G
9. | Understand any related logistic requirements, (including locations of suppliers), and volume requirements (including packaging concerns, density of containers and frequency of shipment). |  |  |  |  | G | G | G
10. | Understand the appropriate requirements of the Program's Work Plan including timing , the APQP Elements, the guidelines for Prototype parts, etc. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | Y | Y | Y | G
[6 empty] | 0 | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Ford | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 3. Craftsmanship (hidden)
|  |  | APQP Element Rating Checklist |  |  | Craftsmanship is an assessment of what the customer sees, touches, uses, hears, and smells. It impacts design and manufacturing, and improves the overall perception of value.
3. Craftsmanship
| FPDS Timing |  | Due Dates
Item | Start | Target | Program Timing | Supplier Timing | Expectations | VP | TT | PP | SOP | 0
1. | KO | --- | #N/A | #N/A | There are NO major Craftsmanship issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future.
2. | KO | SI | #N/A | #N/A | Define the Program Attribute Teams (PAT) cross-functional team for the development and completion of the Craftsmanship Deliverables for the Program. Members include: Vehicle Operations (VO), Vehicle Center Engineering, Assembly Plants, Stamping Plants, Product Design (PD), Plant Vehicle Team (PVT) Engineering, Internal & External Suppliers, Quality, Manufacturing, Advanced Manufacturing Pre-Program Engineering (AMPPE), Purchasing, Marketing, Corporate Design, Research & Vehicle Technology (RVT), and UGC Customer Service Division (FCSD), as applicable.
3 | --- | SI | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process.
4 | --- | SC | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process. (optional)
5 | SI | PH | #N/A | #N/A | Verify carry-over parts are dimensionally correct to the released drawings or files, to ensure compatibility to mating component(s).
6 | SI | PH | #N/A | #N/A | Review the Master Section & Package drawings with Global Craftsmanship.
7 | KO | PA | #N/A | #N/A | Vehicle/Program Craftsmanship requirements developed by the Craftsmanship PAT, have been reviewed and accepted by the Supply Base and other organizations (e.g. Vehicle Opers., Powertrain, etc). Include Craftsmanship VDS, SDS and Implementation Plan.
8 | KO | PA | #N/A | #N/A | Support the program teams, and provide input of issues into the Craftsmanship Implementation Plan. This Implementation Plan will include benchmarking of similar vehicles.
9 | SI | PA | #N/A | #N/A | Attend and participate in Craftsmanship training
10. | SI | PA | #N/A | #N/A | Participate/support the development of the verification strategy for surface prove-out.
11. | SI | PA | #N/A | #N/A | Support the Capability Concurrence Signoff Process: Work to resolve inconsistencies between SRI/F&F/DVA/plant build data.
12. | --- | PA | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
13. | --- | PA | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process.
14. | SI | ST | #N/A | #N/A | Support the PMT development of the SRI (Surface Required Illustration) and/or fit and finish requirements.
15. | SI | ST | #N/A | #N/A | Use the Dimensional Variation Analysis (DVA) process to verify craftsmanship targets are achievable.
16. | PA | ST | #N/A | #N/A | Electronic Math Surface Data (from clay model) is complete in IDEAS and transferred to engineering. (If applicable)
17. | --- | ST | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
18. | --- | ST | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process.
19. | PH | PR | #N/A | #N/A | Participate/support the implementation of the verification strategy for surface prove-out.
20. | PA | PR | #N/A | #N/A | Support the color Harmony process with pictorials and material/grain/gloss/color selection.
21. | ST | PR | #N/A | #N/A | Review Craftsmanship Data Control Verification Models for performance to objective.
22. | --- | PR | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
23. | --- | PR | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process.
24. | --- | CP | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process.
25. | --- | CP | #N/A | #N/A | Develop Craftsmanship Implementation Plan to achieve craftsmanship targets and close gap to target on pre-production builds.
26. | --- | CP | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
27 | --- | CC | #N/A | #N/A | Update Craftsmanship Implementation Plan from pre-production built to achieve production craftsmanship targets.
28. | --- | CC | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process if required.
29. | --- | CC | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
30. | PA | LR | #N/A | #N/A | Update the SDS.
31. | CP | LR | #N/A | #N/A | Verify Craftsmanship Objectives are being met on the Prototype Builds. (FCPA Verification)
32. | --- | LR | #N/A | #N/A | Update Craftsmanship Implementation Plan from pre-production built to achieve production craftsmanship targets.
33. | CP | LR | #N/A | #N/A | Enter final Confirmation Prototype assessments of the Lessons Learned on Craftsmanship into the Corporate Database, and share the information with RVT and other affected organizations.
34. | --- | LR | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
35. | --- | LR | #N/A | #N/A | Participate and/or support Global Craftsmanship Gateway sign-off process.
36. | --- | LS | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
37. | --- | J1 | #N/A | #N/A | Review information in ColorTrax for accuracy and completeness.
38. | --- | J1 | #N/A | #N/A | Rate 1PP and Job1 Product/Vehicles for Craftsmanship confirmation. (FCPA Verification)
Other
Overall | SI | J1 | #N/A | #N/A | Team's Overall Rating of this Element ( G/Y/R )
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | UGC | Supplier | Open | Close | Issues / Comments / Risks | 0: Corrective Actions / Resolution Plan
NOT REQUIRED

## 3. SubContractor APQP Status
|  |  | APQP Element Rating Checklist |  |  | The Subcontractor APQP Status identifies and reports on the condition of an External Supplier or Subcontractor's APQP process. It is required that Internal suppliers (within UGC) & External suppliers cascade APQP requirements to their sub-suppliers or sub-contractors, and conduct APQP reviews as appropriate
3. Sub-Contractor APQP Status
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Sub-Contractor issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Identify the appropriate cross-functional team used to perform and monitor APQP requirements including part suppliers, sister plants, sub-suppliers, system integrators, additional related suppliers, and the customer. |  |  |  |  | G | G | G
3. | Identify "High Impact" sub-suppliers & sister plants based on, but not limited to, the following risk factors: new technologies, new sub-supplier, new facilities, poor quality history, etc. Provide sub-supplier High Impact list to customer for consensus. |  |  |  |  | G | G | G
4. | Develop an APQP Workplan for sub-suppliers and sister plants that supports the supplier's and UGC's program timing. |  |  |  |  | G | G | G
5. | Identify timing, resources, and responsibilities needed to support Advanced Product Quality Planning (APQP), per AIAG requirements, in the workplan. |  |  |  |  | G | G | G
6. | Workplan timing must be represented in a graphical format (e.g. Gantt Chart), and all sub-supplier timing dates for each element are to be adjusted appropriately to complete the requirements to support the Astemo-GAs program timing. |  |  |  |  | G | G | G
7. | Perform APQP reviews with sub-contractors on a regular basis between Milestones, to ensure ongoing communication and progress towards completion. |  |  |  |  | G | G | G
8. | Use APQP Checklists to assess Quality of Event and determine ratings for each of the APQP Elements identified in the Status Report. |  |  |  |  | G | G | G
9. | Obtain or prepare an APQP Status Report for sub-suppliers at each Milestone or other required interval, track sub-supplier APQP status and provide status and relevant backup documentation, to the customer (e.g. Astemo-GA) upon request. |  |  |  |  | G | G | G
10. | Monitor all sub-supplier PSW dates and report to the customer if any fail to meet the Astemo-GA program timing requirements. |  |  |  |  | G | G | G
11. | Verify that sub-supplier's run-at-rate will meet Astemo-GA program requirements for launch, ramp-up and production. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 4. Facilities, Tools, Gauges
|  |  | APQP Element Rating Checklist |  |  | Facilities, tools, and gauges are those additional, new, refurbished, and relocated resources required to produce the product at the customer specified quantity and quality levels. Expectations for this element include but are not limited to planning, statistical and acceptance criteria, lean manufacturing considerations, qualification of equipment, corrective actions, delivery and setup.
4. Facilities / Tools / Gauges
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Facilities, Tooling, or Gauge issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the appropriate cross-functional team and process to identify the Facility, Tooling, and Gauge requirements, necessary to manufacture the customer specified product at designated quantity and quality levels. (Ref. appropriate AIAG manuals) |  |  |  |  | G | G | G
3. | Identify Tooling and Equipment that will be required for the process with particular emphasis on SC/CC's (e.g. torque, welding, etc). |  |  |  |  | G | G | G
4. | Identify Test Equipment and Checking Fixtures that will be required for the process with particular emphasis on SC/CC's (e.g. torque, welding, etc) and develop a timing plan to support the vehicle program. |  |  |  |  | G | G | G
5. | Ensure Tooling and Equipment design has provided for a Flexible System, e.g. Cell Manufacturing, etc. |  |  |  |  | G | G | G
6. | Ensure that Tooling and Equipment design has provided for quick change over. |  |  |  |  | G | G | G
7. | Ensure that Tooling and Equipment design has provided for volume fluctuations. |  |  |  |  | G | G | G
8. | Ensure that Tooling and Equipment design incorporates the recommended actions from the Process FMEA. |  |  |  |  | G | G | G
9. | Ensure that Tooling and Equipment design has provided for mistake proofing. |  |  |  |  | G | G | G
10. | Obtain agreement of acceptance criteria for tooling and equipment between the customer and the supplier of the equipment. |  |  |  |  | G | G | G
11. | Obtain agreement of acceptance criteria for test and checking equipment between the customer and the supplier of the equipment. |  |  |  |  | G | G | G
12. | Establish gauge and test and checking equipment feasibility and accuracy. through Gauge R and R studies. |  |  |  |  | G | G | G
13. | Ensure that an FMEA has been conducted on all equipment and tooling that is new to the process. (Ref. appropriate AIAG manuals) |  |  |  |  | G | G | G
14. | Ensure capable gauges are available to run preliminary Process Capability Studies at the tooling and equipment supplier's facility. |  |  |  |  | G | G | G
15. | Conduct an initial preliminary Process Capability Study at the tooling and equipment supplier's facility, prior to shipment to the customer. (Ref. appropriate AIAG manuals) |  |  |  |  | G | G | G
16. | Develop a training plan that ensures training has been conducted on new/revised tooling and equipment. |  |  |  |  | G | G | G
17. | Ensure a preventative maintenance plan is complete for tooling and equipment. |  |  |  |  | G | G | G
18. | Ensure setup instructions for new tooling and equipment are complete and understandable to the user. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks | 0: Corrective Actions / Resolution Plan

## 5. Prototype Build
|  |  | APQP Element Rating Checklist |  |  | The Prototype Builds element entails the manufacture or assembly of components, sub-systems, systems, or assembled vehicles (e.g. Confirmation Prototype) that will be supplied to the customer and built prior to the 1PP production trial run.
5. Prototype Build
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Prototype Build issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the appropriate cross-functional team to prepare for, and complete the required Prototype Build. |  |  |  |  | G | G | G
3. | Ensure that suppliers are involved, as appropriate, and have received all necessary information with regard to the customer's schedule, prototype quantities and timing. |  |  |  |  | G | G | G
4. | Ensure that the Prototype Build contains correct level parts which meet all requirements. (e.g. Performance, Fit/Finish, Quality, Dimensional, Labeling, etc). |  |  |  |  | G | G | G
5. | Determine the prototype parts required for internal design verification testing, (e.g. Key Life, durability, packaging, function/fit, etc.) in addition to the customer's required quantities. |  |  |  |  | G | G | G
6. | Develop an "Action Matrix" containing all issues found during the build and subsequent lab, plant and road testing, and review it with the team, and appropriate management. |  |  |  |  | G | G | G
7. | Ensure that assignments are made to correct issues found in the build and subsequent road testing. |  |  |  |  | G | G | G
8. | Ensure that Government Regulation, Process Capability, and Craftsmanship issues are included in the "Action Matrix", as appropriate. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 6. Drawings & Specifications
|  |  | APQP Element Rating Checklist |  |  | The Drawings & Specifications element is an evaluation of the development of Targets and Specifications as they are defined to be input to the design process (e.g. VDS/SDS/CDS), and to the Drawings (including all engineering drawings, CAD data, material specifications and engineering specifications.)
6. Drawings and Specifications: Design Information
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Drawings and Specification issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the cross-functional team for the development of the Drawings, Specifications, and Quality Targets including design engineering, process engineering, suppliers, quality, etc., as applicable. |  |  |  |  | G | G | G
3. | ENGINEERING DRAWINGS Identify dimensions that affect fit, function, durability and customer satisfaction. |  |  |  |  | G | G | G
4. | Ensure that Welding Specifications (including Weld Groups or similar weld classifications) are identified and placed on weld illustrations and/or drawings. |  |  |  |  | G | G | G
5. | Ensure that Astemo-GA specifications are communicated to the appropriate engineering functions (including VDS/SDS/CDS) as appropriate. |  |  |  |  | G | G | G
6. | Ensure that all Government Regulations and Safety requirements are identified (e.g. FMVSS/CMVSS) and incorporated into the specifications and drawings. |  |  |  |  | G | G | G
7. | Ensure all potential Significant/Critical Characteristics are identified on the Drawings or attached documents (e.g. DFMEA, SC/CC Lists, etc.). |  |  |  |  | G | G | G
8. | Identify reference dimensions to minimize inspection layout time. |  |  |  |  | G | G | G
9. | Identify sufficient control points and datum surfaces to design functional gages and test equipment. |  |  |  |  | G | G | G
10. | Ensure tolerances and part specifications are compatible with accepted manufacturing standards for gauges and equipment. |  |  |  |  | G | G | G
11. | Identify any specified requirements that cannot be evaluated using known inspection techniques. |  |  |  |  | G | G | G
12. | MATERIAL SPECIFICATIONS Identify special material characteristics, (e.g. affected by temperature, humidity, etc.) |  |  |  |  | G | G | G
13. | Consider material characteristics to minimize handling, storage requirements, and affect to/from the environment. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 7. Team Feasibility Commitment
|  |  | APQP Element Rating Checklist |  |  | Team Feasibility determines whether the proposed design can be manufactured within the guidelines and specifications. A cross-functional design/manufacturing review team is charged with assessing design feasibility. Once workability is established, the Program Organization undertakes the responsibility for the design/manufacturing review process and reassessing feasibility for any design/part change that may occur.
7. Team Feasibility Commitment
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Team Feasibility issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the cross-functional team that will be responsible for identifying the Feasibility Review Process, and the Program Team Members that must Sign-Off on all Feasibility Issues. |  |  |  |  | G | G | G
3. | Ensure that the product has been adequately defined (e.g. application requirements, etc.) to enable feasibility evaluation. |  |  |  |  | G | G | G
4. | Ensure that all Engineering Specifications can be met as written. |  |  |  |  | G | G | G
5. | Ensure that product can be manufactured to tolerances specified on drawings. |  |  |  |  | G | G | G
6. | Ensure that product can be manufactured to meet the ongoing requirements of Cp/Cpk >= 1.67, or the specified Customer requirements (PSW). |  |  |  |  | G | G | G
7. | Ensure that the process design allows for the use of efficient material handling techniques. |  |  |  |  | G | G | G
8. | Ensure that the process design is considered for ergonomic manufacturing techniques, and that all issues are resolved before signoff. |  |  |  |  | G | G | G
9. | Ensure there is adequate facilities/capability to produce product, and consider any potential product/volume changes. |  |  |  |  | G | G | G
10. | Verify that all engineering actions, and quality/reliability targets have been met and signed off. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 8. Mfg Process FlowChart
|  |  | APQP Element Rating Checklist |  |  | The Manufacturing Process Flow is a graphic representation of the current or proposed sequence of manufacturing process. The Manufacturing flow chart can be either in the traditional flow chart format, or depicted in Cycle Line Layouts, Tooling Line Layouts, Plant Layouts, or other appropriate types of layouts, providing all necessary information is included or attached.
8. Manufacturing Process Flow Chart
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Manufacturing Process Flow Chart issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the manufacturing-responsible cross-functional team for the development of the Manufacturing Process Flow Chart which includes manufacturing, engineering, Material Planning & Logistics, Synchronous Material Flow coordinator, assembly, plants, etc., as applicable, and list the appropriate contact names on the flow documents. |  |  |  |  | G | G | G
3. | As a team, decide what format the Manufacturing Process Flow will use (e.g. traditional flow chart, cycle line drawings, tooling line layout, plant layout, etc.), and the additional information the diagram will need to include (e.g. process information, Dynamic Control Planning, etc.) |  |  |  |  | G | G | G
4. | Develop the new part process flow, using surrogate part process flow charts and existing process FMEAs. |  |  |  |  | G | G | G
5. | Illustrate the sequence of production operations, including: part descriptions, inspection, transportation, storage, subcontracted services, and alternate paths (rework, repair & backup). |  |  |  |  | G | G | G
6. | Describe how the product will move within the process (e.g. roller conveyer, slide, containers). |  |  |  |  | G | G | G
7. | Create a key for symbols used in the flow chart. |  |  |  |  | G | G | G
8. | Identify all appropriate operations affecting special characteristics (Critical and Significant Characteristics). |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 9. Process FMEA
|  |  | APQP Element Rating Checklist |  |  | A Process FMEA is a systematic approach used by a mfg. responsible team to assure that potential process related failure modes and their associated causes have been addressed and resolved. The Mfg. Pocess Flow diagrams as well as the Potential SC/Cc's from the DFMEA are used to ensure that the process is analyzed in the appropriate sequence, with all failure modes addressed.
9. Process Failure Mode and Effects Analysis (PFMEA)
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major PFMEA issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the manufacturing-responsible cross-functional team for the development of the PFMEA which includes design, process engineering, suppliers, the plant, etc., as applicable, and list team names on the PFMEA along with appropriate header information. |  |  |  |  | G | G | G
3. | Use the latest AIAG Failure Modes and Effects Manual, and/or Dynamic Control Planning reference, as appropriate. |  |  |  |  | G | G | G
4. | During preparation of the FMEA's, address lessons learned. Review campaigns and recalls (to prevent future recall failures), user & internal plant concerns, similar process FMEA's, things-gone-wrong, warranty data, Failure Mode Analysis, Fault Tree Analysis, and test method prove outs, etc. |  |  |  |  | G | G | G
5. | Identify and list all operation numbers and descriptions from the Manufacturing Process Flow sequentially on the PFMEA. |  |  |  |  | G | G | G
6. | List and describe Failure Modes in physical, technical and measurable terms. |  |  |  |  | G | G | G
7. | Address the impact of failures as applicable to each of the following items: each part, subsequent operation, system, vehicle, customer wants, government regulations and operator safety. |  |  |  |  | G | G | G
8. | Describe potential causes in terms that can be corrected and controlled, for example, people, material, methods, machines, measurement systems and environment. |  |  |  |  | G | G | G
9. | Assign corrective actions, responsibilities, and completion dates to reduce Government Regulations non-compliance or safety issues (e.g. Severity = 9 or 10), high-severity, high-occurrence, high-criticality, and high-RPN (Risk Priority Number) failures. |  |  |  |  | G | G | G
10. | Consider process improvement techniques (DoE, Robustness Methodology, Mistake Proofing (Poka-Yoke), Global 8D/Prevent Recurrence, etc) to develop preventative and corrective actions for Severity ratings of 5 - 8, with an Occurrence of 4 or more and high RPN items. |  |  |  |  | G | G | G
11. | Ensure that all SC/CC's are controlled and placed on the appropriate Control Plans (e.g. Prototype, Pre-Launch and/or Production) or 100 Percent inspected. |  |  |  |  | G | G | G
12. | Provide Process FMEA and updates to appropriate Design Team and Manufacturing activity with any recommendations for design changes. |  |  |  |  | G | G | G
13. | Update the Process FMEA to reflect design and process changes. Include as appropriate: Lessons Learned, reassessment of RPN numbers after corrective actions, addition of new Failure Modes, and corrective actions due to all test failures. Note: Customer approval of PFMEA's are required for all inverted delta parts. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 10. Measurement Sys Evaluation
|  |  | APQP Element Rating Checklist |  |  | The Measurement System Evaluation assesses the variation of the measurement system and determines whether the measurement system is acceptable for monitoring the process.
10. Measurement System Evaluation
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Measurement System Evaluation issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the appropriate cross-functional team to identify the Measurement System Evaluation requirements including dimensional control, quality engineering, process engineering, the manufacturing facility, supplier, etc., as applicable. |  |  |  |  | G | G | G
3. | Use the AIAG Measurement Systems Analysis (MSA) Handbook and appropriate internal procedures to perform the Measurement System Evaluation requirements. |  |  |  |  | G | G | G
4. | Design new, and modify existing Quality Control gauges and test equipment to comply with APQP Requirements, AIAG Measurement System Analysis (MSA), tooling specifications, program specific objectives, and any applicable laws. |  |  |  |  | G | G | G
5. | Check and verify gauges and test equipment for design confirmation and appropriate design levels. |  |  |  |  | G | G | G
6. | Check and verify gauges and test equipment for safety and functionality. |  |  |  |  | G | G | G
7. | Check and verify gauges and test equipment for accuracy and linearity with adequate discrimination. |  |  |  |  | G | G | G
8. | Check and verify gauges and test equipment for repeatability and reproducibility with adequate discrimination. |  |  |  |  | G | G | G
9. | Ensure that gauges and test equipment meet appropriate Safety and Government Regulations (e.g. welding, torque/TPPS studies, flammability, ECM-Electro Magnetic, etc.) |  |  |  |  | G | G | G
10. | Ensure that Improvement Plans have been developed and are in place for all gauge and test equipment that do not meet acceptance criteria. |  |  |  |  | G | G | G
11. | Ensure that gauges and test equipment are re-qualified to criteria detailed in steps 4 thru 7 above, following modification or repair. |  |  |  |  | G | G | G
12. | Perform correlation studies when duplicate gauges and test equipment exist. |  |  |  |  | G | G | G
13. | Ensure that gauges and test equipment are to the latest engineering level prior to the Production Trial Run, and add them to the Pre-Launch Control Plan. |  |  |  |  | G | G | G
14. | Develop gauge instructions and visual aids to assure appropriate use of the gauges and test equipment in production. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 11. PreLaunch Control Plan
|  |  | APQP Element Rating Checklist |  |  | The Pre-Launch Control Plan is a written description of the dimensional measurements and material and functional tests (in-process checks) that will occur after the Prototype Builds and before the Production Builds. This plan should include any additional necessary product/process controls until the production process is validated. Its purpose is to contain potential non-conformances after prototype, but prior to full production (e.g. 1PP and FEU Builds).
11. Pre-Launch Control Plan
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Pre-Launch Control Plan issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the manufacturing-responsible cross-functional team for the development of the Pre-Launch Control Plan which includes: Design Engineering, Process Engineering, Quality, Material Planning & Logistics, Packaging Engineering, Synchronous Material Flow, the plant, etc., as applicable, and list team members or appropriate contact names on the Pre-Launch Control Plan. |  |  |  |  | G | G | G
3. | Develop the Pre-Launch Control Plan using the latest UGC internal procedures, and/or Section 6 of the AIAG Advanced Product Quality Planning and Control Plan manual, or Dynamic Control Planning as appropriate. |  |  |  |  | G | G | G
4. | Review all product and process characteristics, identifying those required for the Pre-Launch Control Plan. |  |  |  |  | G | G | G
5. | Identify and include controlling process parameters that have a direct relationship to the product Special Characteristics, (e.g. Critical and Significant). |  |  |  |  | G | G | G
6. | Define inspection plans for all material and engineering specifications. |  |  |  |  | G | G | G
7. | Verify gages and test equipment are accurate, repeatable, and reproducible with adequate discrimination using the AIAG Measurement Systems Analysis (MSA) Handbook. |  |  |  |  | G | G | G
8. | Include appropriate inspection sample sizes and frequencies on the Pre-Launch Control Plan. |  |  |  |  | G | G | G
9. | Document preliminary process capability requirements, including measurement procedures, techniques and datums. |  |  |  |  | G | G | G
10. | Ensure that Reactions Plans specify the preventative, corrective and containment actions necessary to avoid operating out-of-control or producing non-conforming products. |  |  |  |  | G | G | G
11. | Document Pre-Launch processes that are different from the intended production process on the Pre-Launch Control Plan. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 12. Operator Proc Instructions
|  |  | APQP Element Rating Checklist |  |  | Operator Process Instructions describe the details of controls and actions that operating personnel must perform to produce quality products.
12. Operator Process Instructions
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Operator Process Instruction issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the manufacturing-responsible cross-functional team for the development of the Operator Process Instructions which includes the plant, manufacturing engineering, operators/team leaders, environmental, safety, ergonomics, etc., as applicable. |  |  |  |  | G | G | G
3. | Ensure that initial elements of the process are adequately described and documented in process definition/instructions for use, operator training, and verification of process steps at the Confirmation Prototype Build Phase. |  |  |  |  | G | G | G
4. | Develop a training plan for operators, back-up and repair, Zone Supervisors, and others as required, to ensure proper execution of process, measurement equipment and gauges, SPC, etc. at each build phase, starting with the Confirmation Prototype Build, as appropriate. |  |  |  |  | G | G | G
5. | Use the lessons learned from the Prototype Build to update the process definitions/instructions, and prepare them for use in the Production. |  |  |  |  | G | G | G
6. | Update the process definitions to include specific operator allocation to the process steps in preparation for the Pre-Launch Builds. |  |  |  |  | G | G | G
7. | Specify significant/critical characteristics in the Process Definition, as appropriate. |  |  |  |  | G | G | G
8. | Refer to the current Control Plans for inspection, testing, process monitoring, statistical methods, and reaction plans, as appropriate, in the development of the operator process instructions. |  |  |  |  | G | G | G
9. | Include acceptance & rejection criteria for product and process where appropriate. |  |  |  |  | G | G | G
10. | Ensure that the required tools and gauges with calibration requirements, job set-up, and tool change intervals are documented. |  |  |  |  | G | G | G
11. | Ensure the identification and handling of non-conforming materials is documented. (e.g. plant practice, control plans, etc.) |  |  |  |  | G | G | G
12. | Include the operation names and numbers, part names and numbers, revision dates, engineering levels, and appropriate approvals. |  |  |  |  | G | G | G
13. | Verify process instructions during the Production Trial Run to ensure that they can perform as intended. |  |  |  |  | G | G | G
14. | Include any downstream customer requirements affected by the operator/operation. |  |  |  |  | G | G | G
15. | Use the lessons learned from the past builds to update the process definitions/instructions, and prepare them for use in production. |  |  |  |  | G | G | G
16. | Demonstrate compliance to the training plan at each build phase for the latest level of instructions, including execution of process, measurement equipment and gauges, SPC, etc (Manufacturing facility responsible). |  |  |  |  | G | G | G
17. | Ensure that process definitions/instructions are accessible and visible in the work station area. (Manufacturing facility responsible) |  |  |  |  | G | G | G
18. | Ensure that visual aids are visible and accessible in the work station area. (Manufacturing facility responsible) |  |  |  |  | G | G | G
19. | Maintain and update operator versatility charts/information, and process definition/instructions, on an ongoing basis to assure that operation requirements can be filled by multiple operators. Particular emphasis should be made on SC, CCs/ Government Regulatory operations. (Manufacturing facility responsible) |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 13. Packaging Specifications
|  |  | APQP Element Rating Checklist |  |  | The supplier of a product must ensure that individual packaging for shipment (including interior partitions) is designed and developed. Customer packaging standards or generic packaging requirements should be used when appropriate.
13. Packaging Specifications
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Packaging issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G | G
2. | Packaging Engineering is to participate, along with Logistics (MP&L) and Purchasing, in the selection process of suppliers to ensure that Packaging considerations are provided and understood. |  |  |  |  | Y | Y | Y | G
3. | Ensure that for suppliers ownership of the container is clearly defined appropriately , as well as any other special requirements. |  |  |  |  | G | G | G | G
4. | Ensure that Sourcing (ship points), Transit Modes, and Volumes are understood and optimized for Quality and Total Cost, when analyzing Product Assumptions. |  |  |  |  | G | G | G | G
5. | Define the appropriate cross-functional team to prepare for, and complete the Packaging requirements. Include Packaging Engineers , Design Engineering, Process Engineering, Plant representation (Material Handling), Part and Packaging Suppliers, and Logistics (MP&L). |  |  |  |  | G | G | G | G
6. | Ensure that packaging materials are selected by considering Astemo-GA's environmental requirement. |  |  |  |  | G | G | G | G
7. | Ensure that part and packaging suppliers are involved, as appropriate, and have received all necessary information with regard to the customer's schedule, packaging requirements, quantities and timing. |  |  |  |  | G | G | G | G
8. | Ensure that past issues on similar packaging are discussed and resolved by the team, in development of new packaging. |  |  |  |  | G | G | G | G
9. | Involve the receiving plant during development of the in-plant containers, plant layout, facility requirements, powered/non-powered equipment, linefeed/storage space, environment, and transit modes (rail/truck) to ensure that all issues are addressed, and all Astemo-GA packaging requirement are met. |  |  |  |  | G | G | G | G
10. | Ensure that the status of Packaging development is reviewed at each Design/Program Review. |  |  |  |  | G | G | G | G
11. | Conduct testing of containers (including laboratory testing) to ensure that parts are not damaged or degraded during shipping. Testing example: cross country shipment |  |  |  |  | G | G | G | G
12. | Document and track issues (including part damage, resourcing, recycling, movement, opening removal, Ergonomics, etc.) for resolution of issues and concerns. |  |  |  |  | G | G | G | G
Other | Packaging Data Sheet has been signed by supplier and Astemo-GA |  |  |  |  | G | G | G | G
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | Y | Y | Y | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 14. Prod'n Trial Run
|  |  | APQP Element Rating Checklist |  |  | The Production Trial Run is a validation of the effectiveness of the manufacturing and assembly process, using production tooling, equipment, environment (including production operators), facilities and cycle times. Output of the Production Trial Run is used for Production Part Approval for the manufacturer.
14. Production Trial Run - Internal & External Suppliers
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Production Trial Run issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the manufacturing-responsible cross-functional team for the Production Trial Run including product engineering, process engineering, the plant, suppliers, quality, etc, as applicable. |  |  |  |  | G | G | G
3. | Use all appropriate available data (e.g. surrogate process, etc.) to estimate predicted capacity ]for the production process and further estimate capacity levels. |  |  |  |  | G | G | G
4. | Determine any issues from the capacity analysis that could prevent Run-at-Rate and capacity by the required date, and prepare a resolution plan for all issues. |  |  |  |  | G | G | G
5. | Conduct Production Trial Run using production facility, tooling, equipment and personnel. |  |  |  |  | G | G | G
6. | Conduct Production Trial Run using production operations (e.g. Production operators, inspection, etc.) |  |  |  |  | G | G | G
7. | Conduct Production Trial Run using production packaging. |  |  |  |  | G | G | G
8. | Conduct Production Trial Run using the Pre-Launch Control Plan. |  |  |  |  | G | G | G
9. | Verify operator and process instructions during Production Trial Run ensuring that they can be performed as intended. |  |  |  |  | G | G | G
10 | Document issues noted during the Production Trial Run for assignments and resolution prior to production. |  |  |  |  | G | G | G
11. | Demonstrate to Astemo-GA the ability to produce parts at line rate (Capacity Verification) prior to the program's SOP date. Typically this is completed 4 weeks before System Fill. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 15. Prod'n Ctrl Plan
|  |  | APQP Element Rating Checklist |  |  | The Production Control Plan is a written description of the systems for controlling parts and processes during full production. This document is based on the Pre-Launch Control Plan.
15. Production Control Plan - Internal & External Suppliers
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Production Control Plan issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the manufacturing-responsible cross-functional team for the development of the Production Control Plan which includes members from the plant, design engineering, process engineering, and quality, etc., as applicable, and list the team members or appropriate contact names on the Production Control Plan. |  |  |  |  | G | G | G
3. | Develop the Production Control Plan using the latest UGC internal procedures, and/or Section 6 of the AIAG Advanced Product Quality Planning and Control Plan manual, or Dynamic Control Planning as appropriate. |  |  |  |  | G | G | G
4. | Review all product and process characteristics, identifying those required for the Production Control Plan, and obtain process and design engineering input and concurrence, as applicable. |  |  |  |  | G | G | G
5. | Carry over all identified Significant Characteristics (SCs) and Critical Characteristics (CCs) from the Pre-Launch Control Plan to the Production Control Plan. Additionally, items that need to be monitored by special controls e.g. customer issues, Recalls, Craftsmanship, etc.) must be included on the Production Control Plan. |  |  |  |  | G | G | G
6. | Define inspection plans for those material and engineering specifications that require monitoring. |  |  |  |  | G | G | G
7. | Verify gauges and test equipment are accurate, repeatable, and reproducible with adequate discrimination using the AIAG Measurement Systems Analysis (MSA) Handbook. |  |  |  |  | G | G | G
8. | Include appropriate inspection sample sizes and frequencies on the Production Control Plan. |  |  |  |  | G | G | G
9. | Document process capability requirements, including measurement procedures and techniques. |  |  |  |  | G | G | G
10. | Ensure the Production Control Plan includes the "current controls" from the P/DFMEA's that have not been sufficiently improved in the new design or process, and which still require monitoring in production. |  |  |  |  | G | G | G
11. | Ensure that Reaction Plans specify corrective and containment actions necessary to avoid operating out-of-control or producing non-conforming products. (e.g. 100% hand torque of non-capable processes. |  |  |  |  | G | G | G
12. | Give the customer the opportunity to review and approve the Production Control Plan. |  |  |  |  | G | G | G
13. | Update Control Methods and Reaction Plans to address any issues and Lessons Learned during the Production Trial Run, including counter measures for known capability problems. Note: Customer approval is required for inverted delta parts. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | UGC | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 16. Prelim Process Capability
|  |  | APQP Element Rating Checklist |  |  | The Preliminary Process Capability study is a statistical assessment of the ability of the process to produce product within specification. Refer to the AIAG Production Part Approval Process (PPAP) manual for more details concerning the Preliminary Process Capability study.
16. Preliminary Process Capability
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Preliminary Process Capability issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the appropriate cross-functional team to identify the Preliminary Process Capability requirements including dimensional control, quality engineering, process engineering, the manufacturing facility, tooling supplier, etc., as applicable. |  |  |  |  | G | G | G
3. | Use the AIAG Production Part Approval Process (PPAP), AIAG Statistical Process Control (SPC) Manual and/or appropriate internal Astemo-GA QA manual to perform the Preliminary Process Capability requirements. |  |  |  |  | G | G | G
4. | Establish a plan for performing process capability studies on new or revised processes, Significant/Critical Characteristics (e.g. SC/CC's) |  |  |  |  | G | G | G
5. | Conduct initial Preliminary Process Capability or Gauge R & R studies at the Tooling, Equipment or Gauge supplier and correct any observed issues. |  |  |  |  | G | G | G
6. | Identify any non-capable processes and develop a corrective action plan to achieve capability requirements. |  |  |  |  | G | G | G
7. | Demonstrate correlation between sources of variation, product characteristics and/or downstream operations. |  |  |  |  | G | G | G
8. | Perform Preliminary Process Capability studies after installation in the part manufacturing plant, as documented in the Pre-Launch Control Plan(s) and achieve a minimum Pp/Ppk of 1.67 or as specified by the Customer. |  |  |  |  | G | G | G
9. | For any situations (including torque) where a minimum Pp/Ppk (short term) value of 1.67 or customer specified requirement, plan to establish 100% inspection to assure quality. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 17. PV Testing
|  |  | APQP Element Rating Checklist |  |  | Production Validation Testing refers to engineering testing which validates that products made from production tools and processes meet engineering standards/specifications. All Internal and External Suppliers to UGC are to complete Production Validation Testing as a requirement of the Part Submission Warrant (PSW).
17. Production Validation Testing - Internal & External Suppliers
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major Production Validation Testing issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. |  |  |  |  | G | G | G
2. | Define the appropriate cross-functional team to identify the Production Validation Testing requirements including product design, manufacturing engineering, part suppliers, tool suppliers, plant quality, plant manufacturing engineering, etc., as appropriate. |  |  |  |  | G | G | G
3. | Identify the affected part/assemblies on the production test plan. |  |  |  |  | G | G | G
4. | Ensure that tests are conducted with parts generated from Production Trial Run including parts from alternative paths (i.e. in process repair/rework, and alternative manufacturing processes). |  |  |  |  | G | G | G
5. | Ensure that test data has been reviewed by all the production involved personnel. |  |  |  |  | G | G | G
6. | Initiate a Corrective Action Plan with assignments and conduct follow-up for any/all issues. |  |  |  |  | G | G | G
7. | Ensure that Management has reviewed the Production Validation results and signed-off, as appropriate. |  |  |  |  | G | G | G
8. | Archive the Production Validation results for future lessons learned. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan

## 18. Part Submission Warrant
|  |  | APQP Element Rating Checklist |  |  | Production Part Approval Process is the documented verification that the Internal or External supplier meets all engineering design requirements and the process has the capability to meet these requirements during an actual production run. The Part Submission Warrant (PSW) is the final sign-off that the Production Part Approval Process (PPAP) has been followed.
18. Part Submission Warrant (PSW)
(Astemo) where referenced in this document refers to Astemo Americas, Inc. GA refers to Monroe, GA Plant
Item | Expectations |  |  |  |  | VP | TT | PP | SOP
1. | There are NO major PSW issues/inhibitors, that will create an uncontainable risk now or in the foreseeable future. Note: Quality and Reliability Statement of Work (SOW) requirements are/have been met. |  |  |  |  | G | G | G
2. | Define the cross-functional team that will be responsible for the preparing all evidence for the PSW. |  |  |  |  | G | G | G
3. | Prepare for the PSW using the latest Astemo-GA internal procedures and/or the AIAG Production Part Approval Process (PPAP) manual, as appropriate. |  |  |  |  | G | G | G
4. | Prepare for capacity verification evaluation by understanding the specific requirements of the capacity verification (run-at-rate) sign-off process. |  |  |  |  | G | G | G
5. | Ensure that parts can be produced at line rate (Run-at-Rate) before SOP. |  |  |  |  | G | G | G
Other
Overall | Team's Overall Rating of this Element ( G/Y/R ) |  |  |  |  | G | G | G
[6 empty] | 0 | 0 | 0 | 0
| Instructions: | Consider status of Expectations and then enter Overall Rating for that milestone. Enter open issues/comments/risks & resolution plans below. Rate this element based
on the Expectations that should be complete at the milestone (shaded areas). Future Expectations should be considered when developing a Plan for completion of this Element.
If a particular "Expectations" item is not applicable, enter "N/A" in the Milestone/Team Event column. Additional lines have been left blank, and may be used by Teams to add additional Expectations.
Actions/Tasks to satisfy an Expectation may need to be IN PROGRESS before they become due. Teams may enter "% complete", or similar rating, for their own use in tracking progress/status if desired.
Item | Astemo-GA | Supplier | Open | Close | Issues / Comments / Risks |  |  |  |  | Corrective Actions / Resolution Plan